## Slide 1
Stakeholder Engagement Plan (SEP)

## Slide 2: Contents of a Stakeholder Engagement Plan
Introduction/Project Description (suggested length: 1 page)
  BRIEFLY describe project objectives, components, and location (especially any element which is important in terms of stakeholder engagement)
Brief summary of previous stakeholder engagement activities (1–2 pages)
  Which initial consultations have you already carried out?
  What early feedback have you received from stakeholders regarding how, when and where they would like to be engaged/contacted?
Stakeholder identification and analysis (1–2 pages)
  Is the list broad enough? Does it change over time?
Stakeholder engagement program (3 pages maximum)
  What will the engagement framework look like?
  Which materials will be in the public domain, in which language, where and when will they be disclosed, and where can stakeholder turn to for comments/questions?
Resources & responsibilities for implementing stakeholder engagement activities
  Human resources for stakeholder engagement: Who within the PIU will be responsible for implementing the stakeholder engagement program?
  Financial resources for stakeholder engagement: How will stakeholder engagement activities be budgeted?
Grievance Mechanism
  How will people be able to give feedback/voice possible concerns about the project?
Monitoring and reporting plan (1–2 pages)
  How will you report back to stakeholders?
  How can you engage them in project monitoring?

## Slide 3: Template to Capture Consultation Minutes
Stakeholder (Group or Individual) | Dates of Consultations | Summary of Feedback | Response of Project Implementation Team | Follow-up Action(s)/Next Steps | Timetable/ Date to Complete Follow-up Action(s)

## Slide 4: Stakeholder Engagement and Information Disclosure
STAKEHOLDER IDENTIFICATION AND ANALYSIS OBJECTIVES
Identify project stakeholders:
  Two main categories: Project-Affected Parties and Other Interested Parties.
  Interests and level of engagement can vary among members of each category (and within a given community or household)
Develop an understanding of:
  the different stakeholders’ interests, aspirations and concerns that could be relevant to the project objectives and activities
  the impacts the project could have on different stakeholders, and
  the influence various stakeholders could have on project implementation (including improving design and facilitating progress; or delaying implementation and undermining results)
Also Identify any Project- Affected Parties (PAPs) who may be disadvantaged or vulnerable
Determine how to reach and engage with different types of stakeholders most effectively (e.g. medium, modality, language, location)
Notes: Note: in last bullet, “modality” refers to Focus Groups, one-on-one interviews, town hall meetings, written comments, etc.

## Slide 5: Stakeholders – Example of REDISSE in Angola
Stakeholders likely to be affected, directly or indirectly, by the results of the implementation of the REDISSE project | Stakeholders involved in the implementation of the REDISSE project | Actors influencing the implementation of REDISSE
Ordinary inhabitants/visitors of Angola (their representative organizations/civil society in general) Workers/professionals (both in public and private health care systems) Residents of towns/villages located near health care facilities to be built/rehabilitated. Non-governmental organizations (NGOs) operating at local, regional, national and international levels (including health and environmental organizations) Civil society organizations Local media Vulnerable social groups (e.g., seniors, women, people with disabilities, children, illiterates, Indigenous peoples, Indigenous peoples) | Regional and National Steering Committees (RSC & NSC) respectively Project Implementation Unit (PIU)/National One Health Committee Construction and health facility work/contractors Service and Facility Providers | Provincial government administration Government administration (ministries of health; Planning, Agriculture and Livestock, Environment and Sustainable Development, and Communication) ECCAS General Secretariat Regional Project Coordination Unit Health Inspectorate Environmental Protection Inspection Labour Inspectorate Academics/researchers World Health Organization

## Slide 6: Stakeholder Analysis & Mapping
Influence and Interest Matrix
Where does each of your stakeholders sit on this map?
Low
High
Low
High
INFLUENCE
INTEREST

## Slide 7: Stakeholder Engagement Modes and Techniques
Remain Passive |  | Monitor | Inform | Consult | Collaborate | Empower
Goal | No goal. No | Monitor | Inform or educate | Gain information | Work with | Delegate decision-making on
 | engagement. | stakeholders' | stakeholders. | and feedback to | stakeholders to | particular issue to stakeholders.
 |  | views. |  | inform decisions. | understand issues | 
 |  |  |  |  | and concerns and | 
 |  |  |  |  | formulate joint | 
 |  |  |  |  | responses. | 
Engagement | Stakeholder concern | Media and | Bulletins, letters, | Surveys, focus | Multi-stakeholder | Integration of stakeholders into
Techniques | expressed through | internet tracking. | brochures, reports, | groups, one-to-one | forums, advisory | governance structures, such as
 | protest, letters, media, | Reports from | websites, open houses, | meetings, | panels, consensus | through becoming shareholders,
 | websites, etc., or | other | displays, press | workshops, public | building | members of committees (e.g.
 | pressure on regulatory | stakeholders or | releases, press | meetings, advisory | processes, joint | Grievance Redress Committees,
 | bodies and other | interviews. | conferences, | forums, online | projects, | Community Development groups),
 | advocacy efforts. |  | advertising. | feedback and | partnerships. | taking over responsibility for
 |  |  |  | discussion. |  | aspects of activity.
Meaningful stakeholder engagement ≠ Decide, Announce, Defend (DAD), a top-down, minimally participatory management approach.
Meaningful stakeholder engagement should focus on consultations, collaboration and empowerment of stakeholders, and two-way communication.
Even though some people may protest or complain about the project, any pressure, threats or reprisals against them are unacceptable.

## Slide 8
Allows stakeholders to express their views on projects risks and impacts and mitigation measures – encourages stakeholder feedback
Allows Governments to consider and respond to stakeholder input
Begins early in project planning to gather views and inform project design
Encourages stakeholder feedback – to inform project design and engagement by stakeholders in the identification and mitigation of environmental and social risks and impacts;
Continues on an ongoing basis, as risks and impacts arise
Is based on the prior disclosure and dissemination of information in a way that allows meaningful consultations.
Is culturally appropriate, accessible and understandable to stakeholders
Supports active and inclusive engagement with project-affected parties
Is free of external manipulation, interference, coercion, discrimination, and intimidation
Is documented and disclosed by the Government
Meaningful Consultation

## Slide 9: Stakeholder Information/Consultation Needs
Stakeholder category | Specific stakeholder groups | Key features | Language needs | Preferred means of notification | Specific needs
Rural Zone | The members of the Community do not master the French language | About 80% of the population cannot read/write; Many citizens speak only local languages | Use of local languages – It can vary from village to village | Community network and radio | Afternoon meetings held with the Community (mornings are usually reserved for agricultural activities)
Indigenous peoples or disadvantaged communities | Members of the Community – usually do not master the official national language (Sango) | Distinct culture and language, often marginalized from society | Local languages, varying from group to group | Culturally appropriate means of notification – through a community interpreter and traditional leadership | Distinct cultural practices will imply specific needs – to be identified in the IPPF
Civil society organizations | Various diverse groups | Health/social care service providers Advocacy Organizations | French; Local languages | Information transmitted in writing, radio, meetings | Project activities, information on infectious diseases and disease prevention systems
Media | Various media | Source of information and opinions for other stakeholders | French; Local languages | Information transmitted in writing, radio, television | Project activities, information on infectious diseases and disease prevention systems
Private sector | To be continued during the project phase | Decision makers Workers | French; Local languages (workers) | Written Information and Internet | Information on infectious diseases and systems for prevention, detection, and response to these diseases
Partenaires Techniques financiers | Funders | Shareholders Administrators Officials | French | Written information, meetings | Performance against project indicators (financial, backups, etc.)
Health Project Example

## Slide 10: Stakeholder Engagement Program (Action Plan)
Project Stage | Estimated Date/Time Period | Topic of Consultation/ Message | Method Used | Target Stakeholders | Responsibili-ties
Preparation |  |  |  |  | 
Implemen-tation |  |  |  |  | 

## Slide 11: Budget Template
Budget Category | Quantity | Unit Costs | Times/Years | Total Costs | Remarks
1. Estimated staff salaries* and related expenses |  |  |  |  | 
1a. [E.g., communications consultant] |  |  |  |  | 
1b. [E.g., travel costs for staff] |  |  |  |  | 
1c. [E.g., estimated salaries for Community Liaison Officers] |  |  |  |  | 
2. Events |  |  |  |  | 
2a. [E.g., organization of focus groups] |  |  |  |  | 
3. Communication campaigns |  |  |  |  | 
3a. [E.g., posters, flyers] |  |  |  |  | 
3b. [E.g., social media campaign] |  |  |  |  | 
4. Trainings |  |  |  |  | 
4a. [E.g., training on social/environmental issues for PIU and contractor staff] |  |  |  |  | 
4b.[ E.g., training on gender-based violence (GBV) for Project Implementing Unit (PIU) and contractor staff] |  |  |  |  | 
5. Beneficiary surveys |  |  |  |  | 
5a. [E.g., mid-project perception survey] |  |  |  |  | 
5b. [E.g., end-of-project perception survey] |  |  |  |  | 
6. Grievance Mechanism |  |  |  |  | 
6a.[E.g., training of GM committees] |  |  |  |  | 
6b. [E.g., suggestion boxes in villages] |  |  |  |  | 
6c. [E.g., GM communication materials] |  |  |  |  | 
7. Other expenses |  |  |  |  | 
7a. [insert] |  |  |  |  | 
TOTAL STAKEHOLDER ENGAGEMENT BUDGET |  |  |  |  | 

## Slide 12: Estimated costs of stakeholder engagement activities
Rubriques du budget (à titre d’illustration) | Quantité | Coûts unitaires | Fréquence annuelle | Coûts totaux | Remarques
1. Rémunération du personnel et dépenses connexes |  |  |  |  | 
2. Événements |  |  |  |  | 
3. Campagnes de communication |  |  |  |  | 
4. Formations |  |  |  |  | 
5. Enquêtes auprès des bénéficiaires |  |  |  |  | 
6. Mécanisme de gestion des plaintes |  |  |  |  | 
7. Autres dépenses |  |  |  |  | 
BUDGET TOTAL POUR LA MOBILISATION DES PARTIES PRENANTES : |  |  |  |  | 
Budget headings (for illustrative purposes) | Quantity | Unit costs | Annual frequency | Total cost | Observa-tions
1. Staff compensation and related expenses |  |  |  |  | 
5 Community Liaison Officers in 5 municipalities @ $500 per month | 5 | 6000 | 5 | 150 000 $ | 
Social Media Consultant (6 months per year, $1000 per month) | 1 | 6000 | 5 | 30 000 $ | 
2. Events |  |  |  |  | 
5 meetings to present the project (room rental, catering, printing) | 5 | 2500 | 1 | 12 500 $ | 
22 quarterly awareness-raising meetings | 88 | 100 | 5 | 44 000 $ | 
3. Communication campaigns |  |  |  |  | 
Communication materials, public relations file (posters, brochures) |  |  |  | 30 000 $ | 
4. Training |  |  |  |  | 
Training on environmental and social issues (including gender-based violence) for supplier and contractor staff/consultants |  | 1000 | 5 | 5 000 $ | 
5. Recipient Surveys |  |  |  |  | 
Public/project affected persons perception survey |  | 2500 | 2 | 5 000 $ | 
6. Grievance Mechanism |  |  |  |  | 
Grievance Management Mechanism Database/GIS | 1 | 20 000 | 1 | 20 000 $ | 
Suggestion boxes | 30 | 50 | 1 | 1 500 $ | 
Municipal Grievance Committee Formation | 5 | 100 | 5 | 2 500 $ | 
OVERALL BUDGET FOR STAKEHOLDER ENGAGEMENT: |  |  |  | 300 500 $ | 

## Slide 13
Back up slides

## Slide 14: Stakeholder Engagement and Information Disclosure: Why?
Allows to ask for and receive diverse views regarding project design, implementation risks, impacts, and mitigation measures.
Helps to develop strong, constructive and responsive relationships with people impacted by the project.
Can support project supervision and help identify potential environmental and social issues early.
Can improve the environmental and social sustainability of projects, the project’s acceptance and its outcomes, and contribute to successful project design and implementation.
Key Objective : Establish systematic approach to stakeholder engagement that help Borrowers identify stakeholders and build and maintain constructive relationships with them, in particular project-affected parties.

## Slide 15: Engaging Vulnerable or Marginalized Groups
People living in remote or hard-to-reach areas
People with limited digital connectivity
People with limited access to communication media —newspapers, TV, radio, etc.
People with limited transportation options to gain access to documents or participate in meetings
People with low literacy levels
People with low technical literacy, particularly for complex technical project
Linguistic minorities
People with disabilities
Women, children and survivors through organizations advocating for their rights, etc.
Sexual Orientation and Gender Identity minorities through organizations advocating for their rights
Elderly or youth
Women and girls
People disadvantaged based on economic or occupational status
Indigenous peoples, ethnic, racial or religious minorities
People with a specific civil status (migrant, refugee…)
Internally Displaced Persons
Vulnerabilities linked to access issues ►
Other types of vulnerabilities (literacy, identity, age, status, etc.) ►
How can these vulnerabilities be addressed through different engagement approaches?
Account for Types of Vulnerability and adapt Engagement Measures Accordingly

## Slide 16: Stakeholder Engagement Program
Phase du projet | Parties prenantes visées | Thème(s) de la mobilisation | Méthode(s) utilisée(s) | Lieu/ fréquence | Responsabilité
… | … | … | … | … | …
 | … | … | … | … | …
Tips: Tailor stakeholder engagement activities to project phases Specify the frequency of engagement and communication activities with different stakeholder groups Determine within the PIU who is responsible for each aspect of stakeholder engagement and information dissemination
Project Phase | Targeted stakeholders | Engagement Theme(s) | Method(s) Used | Place/ frequency | Responsible entity
Preparation and implementation of the Resettlement Action Plan (RAP); Detailed Design | Persons affected by land acquisition People living in the project area Vulnerable households | Land Acquisition Process Assistance in gathering the necessary official documents for rapid registration in the land registry Rates and methods of compensation Project scope and rationale Environmental and social principles of the project Resettlement and livelihood recovery options Complaint Management Mechanism Procedures | Public meetings Training/Workshops Meetings for women and vulnerable people only Communication in the press/on social networks – Facebook, WhatsApp Dissemination of written information – brochures, posters, leaflets, website Information Offices in Municipalities and at Headquarters Complaint Management Mechanism Survey of Persons Affected by the Project – After Relocation Is Complete Community radios Town criers | Project presentation meetings in municipalities Monthly meetings in affected municipalities and villages Survey of people affected by the project in the villages concerned Press/social media communication (if required) Information offices offering brochures/posters in affected municipalities (on an ongoing basis) | UEP (Environmental and Social Affairs Team, Community Liaison Officers, Land Acquisition Department); consultant for PAR; Municipal Complaints Management Committee
 | … | … | … | … | …
SEP example involving Resettlement issues